| #### Legal Name: | #### Jersey City Redevelopment Agency |  |  |
| --- | --- | --- | --- |
| #### Report Period (from/to): | #### February 28, 2011-February 27, 2014 | #### Grant Number: | #### CCPNJ0035-10 |
| #### POC: | #### Benjamin Delisle, Director of Development | #### AOR: | #### Christopher Fiore, Assistant Executive Director |

- ACCOMPLISHMENTS

- Please describe your progress relative to the milestones scheduled during this reporting period. Details on accomplishments throughout the grant period were provided in prior semi-annual reports, and the major project accomplishments included: - Holding five community meetings, which included a total of nearly 100 total attendees; - Development of an Infrastructure Financing Plan, which provided a financing structure to help guide the development of Canal Crossing. Topics addressed in the plan include build-out capacity, tax increment financing, and potential funding sources, among other subjects; - Development of a white paper that outlined a framework for land readjustment in Canal Crossing. Under land readjustment, property owners participate in a public-private joint venture where the municipal redevelopment authority pools, rezones, and redistributes the land or shares in a common land trust amongst the contributing property owners. The municipal redevelopment authority then provides redevelopment rights to the property owners along with the new parcels or shares. The property owners may monetize these assignments through sale of their portion of the property and the associated up-zoned redevelopment rights to developers, and/or by retaining an equity stake in the redevelopment; - Development of boundary and topographic surveys as well as legal descriptions and deed submittals covering all of Canal Crossing; - Development of information on environmental constrains impacting Canal Crossing, particularly given the presence of brownfield sites in this industrial area; and - Development of two light rail studies. These included the study discussed in the original grant workplan, which focused on a potential new light rail station. The second study addressed potential improvements to the existing light rail station on Garfield Avenue. Additional details regarding the many milestones associated with Task 3, which is being funded entirely by the corresponding DOT TIGER II grant can be found in the project engineer’s weekly progress reports as well as the performance narratives submitted with each reimbursement request. - Please describe the percentage completion for each of the major task categories identified in your negotiated workplan. Task 1, legal counsel & real estate: 100% Task 2, pre-design survey & engineering surveyor: 100% Task 3, planning & design: 100% (note Task 3 was the only task entirely funded by the corresponding DOT TIGER II grant) Task 4, light rail study: 100% - Please describe your progress with contract and sub-award management, including any issues you are experiencing or anticipating: The project progressed on schedule and is now complete. - Please provide an update with regards to the project’s match/leverage commitments. The total match associated with this grant is $65,875. The $15,000 cash match required as part of Task 2 was met in a prior reporting period. Additional in-kind match amounts, particularly for team members from New Jersey Transit, were reported following DOT’s approval of the cost share budget modification request for the corresponding TIGER II grant in December 2013. As a result, the $50,875 required in in-kind services has now also been met and documented. Thus the full $65,875 match commitment has been met. In fact, we even exceeded the requisite match amount, for a total of $79,975.90, to include the $15,000 cash match and $64,975.90 in in-kind services. - Please identify newly developed or existing collaborations and the progress they experienced during the reporting period. Notably, community outreach meetings were held in early 2014 both before and after this HUD grant ended (outreach held post-February 27, 2014 was funded by the corresponding DOT TIGER II grant, which ended on March 31, 2014). During the course of community outreach it was determined that real estate brokers need to be part of the conversation with property owners. More brokers will be included in future Canal Crossing meetings. The JCRA will also work to identify developers for Canal Crossing. Further, the JCRA worked to engage the new City administration that took office in July 2013 in the project. Despite the closeout of the HUD and DOT grants, the JCRA will continue to work on engaging the administration in the importance of the redevelopment of Canal Crossing. - Please describe progress with outreach, engagement, and decision-making activities targeting populations traditionally marginalized in the planning process (include costs spent on these activities): Canal Crossing predominantly includes large tracts of vacant brownfields and many businesses, and outreach focused residents in surrounding neighborhoods and business/ property owners within Canal Crossing. Outreach is a major component of Task 1 of the project. As such, the JCRA’s Canal Crossing website was updated as needed to include weekly progress reports, meeting minutes, and project deliverables. Community meetings were also held in March 2013, October 2013, January 2014, and March 2014. In total, these meeting included nearly 100 attendees. The overall budget for Task 1 was $23,900. Outreach will continue now that the grant-funded work is complete.

- CHALLENGES AND EFFORTS TO OVERCOME THEM:

- Scheduled Milestones/Targets that were not achieved: N/A - Management deficiencies: N/A - Deviations from the Work Plan N/A - Detail the actions you will take to address identified deficiencies or workplan deviations described above (include what is to be done, who is responsible, and when it is due). N/A

- ANALYSIS OF WORK TO DATE

  - What lessons are you learning as you move forward that will strengthen this process?  What assumptions about planning for sustainability are being confirmed and which are being challenged as you move forward? Can you apply these lessons into your work in real time?

One lesson learned is that private investment in Canal Crossing will be highly dependent on both the cost and phasing of infrastructure improvements in the area.  This is why we requested that HUD and DOT approve the development of an Infrastructure Financing Plan under Task 1.  This plan includes very valuable financial planning information relevant to moving forward with the redevelopment of Canal Crossing.  For this project, we did not approach it with specific assumptions about sustainability; redevelopment of this former industrial area with large tracts of vacant brownfields is sustainable by definition.

  - Are you staying on target for the overall goal of the initiative? To what extent are the overall program outcomes and workplan deliverables a helpful reference point?

Yes, although the corresponding DOT TIGER II grant was awarded a no-cost time extension to extend the grant end date from September 30, 2013 to March 31, 2014 in order to bring the time period in line with the HUD grant.  The overall goal of the project was develop infrastructure-related informational components that will be needed to redevelop the Canal Crossing neighborhood.  Each of the project’s deliverables has provided valuable information that can be provided to both the community and developers to allow for thoughtful and deliberate redevelopment of the area.  These deliverables will not just serve as reference points but also as actual documents that will be referenced in the future as needed.

  - What evidence do you have that this plan will translate to concrete impact and actual implementation in the months and years to come?  Has the quality of the implementation taken on a different character because of the approach that you have taken in the planning process (e.g., emphasis on engagement and equity)?

The deliverables that are resulting from this grant and the corresponding DOT TIGER II grant—including the light rail studies and designs/plans/cost estimates for the many infrastructure components—are supplying the JCRA with valuable information needed to move forward with the redevelopment of Canal Crossing.  This information can be provided to developers in order to inform their approach to redevelopment of whatever site or block in which they may invest.  The quality of the implementation has not taken on a different character because of the approach that the JCRA has taken in the planning process.

- NEED TO AMEND THE COOPERATIVE AGREEMENT:

|  | Yes/No | Explanation/Reason for Deviation |
| --- | --- | --- |
| Scope | Yes | In October 2012, HUD approved the addition of a second light rail study under Task 1. This resulted in a study of the existing light rail station on Garfield Avenue. In December 2013, DOT approved the following scope revisions: - Development of an Infrastructure Financing Plan under Task 1; - Inclusion of the actual wage rates and additional team members whose time was counted toward the in-kind requirement; and - Extension of the TIGER II grant through March 31, 2014 and associated revisions to the deliverables schedule, primarily with the DOT-funded Task 3. HUD deferred to DOT’s approval process for approval of these scope revisions. |
| Schedule | No |  |
| Budget | No |  |
| Key Staff or AOR | Yes | In late 2013, the JCRA notified HUD of a change in the AOR. |

- Need for Technical Assistance

The JCRA does not have a need for technical assistance but thanks HUD for all of their support and guidance during the course of the project. We greatly appreciate HUD’s flexibility. During the course of the project, we realized we needed to develop an Infrastructure Financing Plan and a study of the existing light rail station on Garfield Avenue. Neither of these studies was included in the original grant workplan, but following HUD and DOT’s approval, the development of these studies ultimately provided incredibly valuable information for all project stakeholders.

Public reporting burden for this collection of information is estimated to average 1.5 hours. This includes the time for collecting, reviewing, and responding to questions. The information is being collected for mandatory semi-annual reporting and will be used for tracking implementation of HUD-approved work plans. Response to this request for information is required in order to receive the benefits to be derived. This agency may not collect this information, and you are not required to complete this form unless it displays a currently valid OMB control number. No confidentiality is assured.