- What lessons were learned during the period of performance that will improve the implementation of the plan developed during your grant process?  What assumptions about planning for sustainability are being confirmed and which are being challenged as you move forward?

- Assumptions Confirmed by Actual Events

  - A champion(s) is needed; one that understands and believes in the process and outcomes; one willing to engage new partners; one not using process to promote a personal agenda.

  - The plan must be based in facts, strategies must have implementers and resources must be identified for implementation to have any traction.

  - There will be conflicts and complications that threaten to de-rail the process and the plan.

  - Misperceptions about the plan can persist and threaten final acceptance and implementation.

  - The first year should be ‘under the radar’ for data collection, without creating unfulfilled expectations.

  - It will be difficult to draw people away from their local perspective and to think regionally

- Assumptions Challenged and Proven Not True

  - People are tired of planning

  - Three years is too long to plan

  - People cannot understand/appreciate how land use patterns affects community opportunity

  - People cannot understand how transportation, housing and the work force are inter-related

  - Business leaders would understand/appreciate the consequences of low wages and low opportunity

- What evidence do you have that this plan will translate to concrete impact and actual implementation in the months and years to come?  Has the quality of the implementation taken on a different character because of the approach that you have taken in the planning process (e.g., emphasis on engagement and equity, sustainability framework, etc.)?

- Evidence of Actual Implementation

  - Growing requests for presentations, use of data

    - MDEQ/RESTORE planners have turned to the Plan for the data, tools and recommendations to leverage the planning/funding for RESTORE

  - Interest in re-convening committees

    - Economic Development and Food Systems

    - Water Component to be introduced to a conservation group to advance the Plan component

  - Agreement to fund first year housing coalition through Renaissance

  - MPO integrated sustainable transportation component into the annual work program and using scenario tools for development of the long range transportation plan

- Character of Implementation

  - Originally thought the focus would be on creating urban design/activity centers for improving quality of life;  the focus became the workforce/living wage to raise the level of prosperity

- What compelling stories encapsulate the work you of your grant? Which successes, innovations, milestones, and other anecdotes that demonstrate the importance of the work?

- MDEQ food waste task force was formed during the first year of the Plan

- MDEQ/RESTORE relying on the work of the Plan

- Scenario model to be used to populate forecasts for the long range transportation plan

- Regional housing coalition under formation

- West Gulfport creating work force development proposal

- East Biloxi creating community plans following the livability principles

- Requests for PSS have been increasing

- Gulf Coast Business Council requesting presentation to guide their committee formation

- How did the federal partnership support or advance your planning effort? What opportunities were missed? What more could be done? How can federal agencies be helpful in implementation?

- Federal Support Helped Advance the Work

  - GTR provided consistent oversight and offered thoughtful advice and sound guidance, constructive feedback throughout the three years

  - Extensive education and training on sustainability planning and leadership through workshops, webinars and the annual convening

  - Targeted capacity building to overcome challenges and reinforce the work being done at the local level with professional expertise under contract (to HUD)

- Opportunity Missed to Support the Grantees

  - Convene the grantees at start of grant award to help guide the development of the work plan; layout the policies, goals and deliverables required by the federal agencies; establish peer groups and mentors among similar projects

  - Eliminate the Logic model

- Federal Help to Support Implementation

  - Provide guidance/ peer exchange on how to plan and organize for implementation at the start of the planning

  - Make certain the state rep is on the same page with the DC office on matters of involvement/support and involvement/disruption.

  - Reduce the review/approval time of the final report so not to stop the rollout of the plan at the local/regional level

  - Encourage all three federal departments to highlight the success of the plan development and notify state agencies of the importance of the final plan.

- What do you think it will take to succeed in effective implementation of your plan? If money, please be specific about the type of money that would be most helpful. If other resources, please describe how they could support your work.

- Transition Funding

- Federal Recognition

- Continue Capacity Building

- Tie federal funds to maintaining plan (just as DOT does with MPOs)

- What are the key milestones that should be tracked as your plan moves to implementation?

- Creating an indicator gauge to monitor progress

  - Strategies

  - Policies