| #### Legal Name: | #### Northwoods NiiJii Enterprise Community, Inc. |  |  |
| --- | --- | --- | --- |
| #### Report Period (from/to): | #### February, 2011 - August, 2014 | #### Grant Number: | #### WIRIP004310 |
| #### POC: | #### Patricia O’Neil | #### AOR: | #### Patricia O’Neil |

- ACCOMPLISHMENTS

- Progress and Accomplishments by Task - Improve Demographic Baselines 1.a Establish Comparable Tribal Demographic Baseline Data Completed. East Central Wisconsin Regional Planning Commission has prepared standard baseline regional planning data for three counties has been provided these data as in-kind to the project. University of Wisconsin Population Center, also as in-kind to the project, has preparing data tables and maps using available secondary data and information on assets generated from focus groups. They have also generated baseline data tables for a 5 County region and the livability principals upon which to monitor Strategic Plan progress. Time series demographic information and projections for comparative communities on population and economic indicators has been completed. A demographic summary report has been produced and presented to the Enterprise Community Board. North Central WI Regional Planning Commission is utilizing this data to supplement their demographic analysis in the production of the strategic plan. This activity is complete. 1.b Improve Lac du Flambeau Demographic Data Collection abilities and complete Comprehensive Strategic Plan Completed. Software and hardware needs to implement the Tribal Census were ascertained, quotes obtained and Tribal Data Resources (TDR) chosen as the vender. Software and hardware have been purchased and installed. Tribal Census staff were hired after two rounds of interviews, criminal background checks and drug testing. Staff occupy the Lac du Flambeau Planning office. TDR trained Census and IT staff in software operation and held a webinar for all tribal program staff in uses of expanded data network. The program has been installed on the Tribal server for program access and data on tribal membership names and addresses have been uploaded. Notice of Census initiation was posted on the tribal website. Calls and letters went out to tribal members announcing the tribal Census. Census workers have updated 2000 records. A final demographic report and final map was produced with the data updated as of the end of the grant. Work from here for ward will be in revision and updates of the database. An area of weakness was identified in the response levels associated with income questions, and since this information is vital to garnering future “poverty” resources, it is a worthwhile endeavor to extend the census activity until statistical significance is reached in the collection of income data. A proposal for future funding has been submitted to the Lac Du Flambeau Tribal Council to build this function into their administrative budget. - Seed Catalytic Projects in the Existing NiiJii Regional Plan 2.a Design Mole Lake Affordable Multi-family Housing Units Completed. The project site was located as the Bishop Lake Subdivision. A site plan was created and this information was transmitted to the GTR for environmental review. The Sokaogon Chippewa Tribal Housing Department performed an Environmental Assessment on the site and this has been transmitted to the GTR along with maps and site plans. A public hearing was held February 2012 to assist in developing project specifics and recruit participants. To date the project participant list includes 25 families as potential home-owners, and 15 families in need of rental properties. A list of potential applicants for project housing has been developed and is available at Tribal Housing. Under the first phase of the plan, a $1.2 million project is planned to include 2, 3, and 4 bedroom single family green homes totaling 30, a playground and an emergency services support facility. Six (6) units will be for residents <30% LMI, 5 units for 50% LMI, and 5 units for 60% LMI. An architect was contracted, produced preliminary plans, an energy efficiency analysis, and a cost proposal, as well as provided assisted with details necessary for grant seeking. The architectural RFQ was published and the tack sheet submitted to the GTR. Also submitted were the RFQ and architects list. Design Coalition of Madison WI was selected for the work, with an excellent background in green design. The contract bidding, architectural and site plans were submitted to the GTR. In addition to preliminary green designs the architect produced an energy analysis for the project. An unsuccessful application for Phase 1 of the project was submitted for WI Housing and Economic Development Authority (Wheda) Tax Credits in January 2013 through Travois. It was re-submitted and awarded in 2014. Currently, the sites have been lotted off and 10 basements have been installed along with water and sewer hook-ups. Construction will re-commence after the winter season. Phase II will be pursued at a later date to include green duplexes. The number (8 - 30) will be dependent on start-up capital and funding availability. The duplexes will be offered for sale to the 25 families on the homeownership list who will then rent the second unit to the 15 family list of participants in need of rentals. The mortgages will be private and the maintenance of the houses will be the responsibility of the homeowner. Continued homeownership training will be pursued. This model will meet the objectives as specified in the Sokaogon Chippewa Community Comprehensive Strategic Plan and should bring homeownership rates on par with other Reservations in WI. The Housing Department has determined that their immediate need is for single family green homes, which will be the first focus of efforts. Procedures for Tribal Housing project operation are in place. Tribal Housing has reviewed the model for tribal green housing ordinances presented by HUD. Finalization of any ordinance changes will be beyond the scope of this grant, however, housing policy changes would occur after the completion of the Mole Lake Energy Plan. 2.b Expand Supports to Small Businesses Completed. Codification of Policies and Programming for the Small Business Training and Technical Assistance Program conducted by Shawano County Economic Progress Inc. (SCEPI) have been developed and transmitted to the GTR. A USDA RBEG Grant was awarded for $89,000 to provide capital to small businesses participating in the program. The award documents were transmitted to GTR. $26,000 in Community Foundation Grants and $300,000 from the City and County revolving loan funds have also been dedicated to complement this initiative. A SCEPI micro-loan fund and business support program are being marketed throughout Shawano County to attract small business development projects. A roster of technical assistance is provided with each report and invoice that identifies the numbers of participants recruited to date, hours and type of technical assistance consultation, the number of jobs committed by recipient businesses and the number of jobs actually realized from start up or expansion. Recruitment of businesses to participate in the program will continue throughout the life of the project. The roster of technical assistance provided shows that consultations resulted in 919 TA visits and 205 new jobs realized as of the close of the project in November 2013. Wisconsin Film and Bag is an example of a one green company benefitting from this project. Due to assistance, they were able to create new jobs while taking tons of plastic out of the environment through an innovative recycling production technique. 2.c Indian Bowl Cultural Facility Completed. A preliminary market study was completed by Innovative LLC. This was a go-no-go analysis of the feasibility of the region supporting a cultural arts facility in the Northwoods. The outlook was positive. We obtained a sole source waiver in order to contract with Innovative further for more detailed feasibility/business plan proforma work which was also completed. An RFP for a consultant experienced in operations of Cultural Facilities was developed to solicit bids for the development of detailed business and operations plan for the facility. The RPP was advertised. Three quotes were obtained. Arts Space of Minneapolis was chosen. A contract was signed. A site visit and several and follow up meetings ensued. A business scenario plan was produced identifying break even operations and this was forwarded to the GTR. We worked with Sandra Gibson, a capacity builder from the DeVoss Arts Management Institute, on an artistic program plan, which is now complete. The Gibson consultation is funded under a Ford grant and informs both the business feasibility and the architectural design specs. A video and website were produced (using funding from the Ford Foundation) to aid in generating public understanding and support for the project and to aid in a capital campaign. Find this at www.indianbowlproject.org HVS, a marketing and advertising firm from Green Bay was selected to perform a fundraising feasibility for the project. Their work identified and interviewed major donors in the local area and launched the capital campaign. A Tribal Corporation (non-profit) has been established and a 15 member Board of Directors has been recruited to manage the facility and launch the capital campaign. The Board hosted several community information meetings, two fund-raising events, a survey and presented to several visiting funders. To date contributions from private donors and foundations near $428,000 mostly for the capital campaign. NiiJii is serving as fiscal agent for the accumulation of contributions toward this initiative until such time as the corporation receives 501 c 3 status. Fund seeking is underway. To date $1.5 million has been raised for pre-development and construction, $107 thousand has been awarded for programming and $11 thousand has been contributed in in-kind services for capacity building. An application to HUD's Rural Innovation Fund in the amount of $3 million was submitted but declined. An NEA Art Space application in the amount of $300,000, an NEA Our Town grant and an NEA Art Works application were submitted but all declined. A HUD-ICDBG application in the amount of $600,000 was awarded for construction. A letter of interest to NEH for an Executive Director to lead a capital campaign was submitted but not invited to apply. An application for construction for $6,000,000 has been submitted to the State of WI for Gaming Fund allocation. A $2,000,000 application to Art Place is pending. An application to the Potawatomi Tribe in the amount of $10,000 was awarded for programming. An application to Ford’s agent Leveraged Investments in Creativity (LINC) was awarded in the amount of $100,000 to complete pre-development efforts, some architectural design and develop a fund-raising plan for this facility. Two additional grants from Ford Foundation ($3,600) and LINC ($5000) were granted to fund a cross-training exchange between the Indian Bowl Board of Directors and an established cultural center in Olympia, WA, the Long House. Two additional grants from the Performance Network funding by the Ford Foundation were awarded to develop arts and culture center capacity through executive exchange ($2,000 and $4,600) A commitment of $300,000 has been secured from the Lac du Flambeau Band as match funding for construction. A Letter of Inquiry to Art Place, a consortium of funders, did not result in an invitation to apply. An application to the Turkish Coalition of America in the amount of $985,500 was also submitted and is still pending. An application to the Shakopee Sioux is in queue three years out. We submitted a preliminary WHEDA New Markets Tax Credit Application in the amount of $464,200 that has been approved as a 2% loan with a 10-year balloon loan payment. The Board has declined this offer. HUD Sustainable Communities Capacity Building Program awarded Minnesota Housing Partnership $100,000 for architectural design for the project. NiiJii will serve as sub-recipient. Lac du Flambeau Planning Department will access BIA Roads Funding as necessary for parking lot, side walk and road work ($250,000). An application was declined with HHS Office of Community Services for $100,000 for construction. Margaret A. Cargill Foundation awarded $1,200 to be dedicated toward construction. National Endowment for the Arts awarded $20,000 for programming one of which outputs includes new Museum doors (attached to the Indian Bowl) painted in the traditional Ojibwe Style. A USDA Rural Business Opportunity Grant and a USDA Rural Business Enterprise Grant were was submitted but denied. A USDA Rural Community Development Initiative Grant was awarded for $99,000 to build Board and Staff Capacity. $3,000 has been contributed by NiiJii’s ANA Arts Program toward development of a funding plan for the facility. A Kennedy Center NxGen III capacity building application was submitted but denied. A Wisconsin Arts Board grant in the amount of $3,100 was awarded to commence development of cultural theater curriculum for programming at the new facility. 2.d Design Mole Lake Fire and Safety Building Completed. A site was selected. Map and site information were forwarded to the GTR and shared with the HUD Environmental Officer. A preliminary EA was performed by the Sokaogon Chippewa’s Environmental Officer. A schematic design was obtained from another township to use for the purposes of discussion regarding space needs and costs. Conflict surrounding a realistic facility size arose and was resolved. Preliminary architectural services were solicited under a bidding process and Architecture North was selected. RFQ, RFP, Bidding Selection Process and Evaluation documentation were forwarded to and approved by the GTR. Preliminary Architectural drawings, elevations and cost estimate have been completed. A funding plan has been developed. A grant was submitted to FEMA Resiliency Fund for an emergency services coordinator, but declined. A HUD ICDBG application in the amount of $850,000 was developed for the HUD FY2013 funding cycle, however, Tribal Council elected not to submit it for two reasons. Due to their financial standing they do not have the match requirement for funding and they are concerned about the ongoing costs of the facility in terms of maintenance, staffing and programming costs. Tribal Council called for the preparation of operational cost budget with projections. Turnkey Economic Development Solutions, LLC & Strategic Development Resources, Inc. was hired to prepare the feasibility and operation cost analysis. Due to the magnitude of this contract ($2,000), no bidding process was necessary. The study was completed and presented to the NiiJii Board and the Sokaogon Chippewa Tribal Council. Based on the study, the Tribal Council has decided to pursue further development of the project and access their Trust for needed match funding for training of firefighters. The Forest County Potawatomi Foundation awarded a grant for fire fighter training in the amount of $30,000. - Fill Gaps in Planning In addition to the below contracted tasks and outside of this cooperative agreement we have completed a Rural Transit Plan for the Lac du Flambeau Band, recruited staff and drivers, and are now operational. 3.a Complete Mole Lake Energy Audit, and Energy Plan Initial assessment has identified cost savings from energy efficient technology installation and energy efficiency practices to yield the biggest immediate return to the Sokaogon Chippewa Community. WI Focus on Energy, a State Agency, conducted building audits at no cost on the four major governmental buildings comprising the Sokaogon Chippewa Reservation. They recommended Condensing Boiler controls and technologies and maintenance practices. Their summary report along with detailed technological recommendations has been forwarded to the GTR. WI Public Service Agency compiled historic energy use data on all Mole Lake service destinations. Some preliminary work had already been done previous to this cooperative agreement to research alternative energy opportunities available to the Tribe, however, energy consultants were be procured to perform a more extensive assessment. An RFQ was developed and the work bid out. H&H was selected as the contractor. The bidding and selection documents have been forwarded to the GTR. The H&H contractor has completed an extensive review of alternative energy options adapted for Tribal needs and a final report and Energy Plan has been published, presented to Tribal Council, and adopted. The Tribe sent two members, the environmental officer and the housing director to attend training on Level 1 Infrared Thermography training for the fundamentals of energy efficiency assessments in housing. The certification, conducted by Fox River Systems in Minneapolis. MN on April 30 - May 5, 2012. This increases the Tribe's capacity to perform the housing energy assessments and sell services to nearby communities who may also demand these services. Housing audits commenced and are likely to proceed beyond the life of this cooperative agreement, now that staff have been trained. 3.b&c Complete Menominee Land Use and Transportation Plans Completed. A Planning Team was established. A list of tasks, activities and timelines were established and forwarded to the GTR. An RFP for a Planning Consultant was developed. East Central Wisconsin Regional Planning Commission was contracted January 19, 2012. Meetings with GTR resulted in combining task 3.b Menominee Transportation Plan with task 3.c Menominee Land Use Planning so that the two activities will be done in tandem. Work Plans for the Project and Gantt Charts were drawn up and transmitted to the GTR. A Community Participation Plan was drafted, approved by the Menominee Department of Community Development and implemented. The consultant compiled baseline data, completed demographic overview, public participation, vision, goals, and objectives sections, existing systems, systems analysis, traffic forecast, GIS decision transportation support, GIS, recommendations, environmental justice, environmental mitigation, financial analysis and monitoring and evaluation sections of the report in coordination with various stakeholders. The contractor has completed the work and the Menominee Tribe is very happy with the output. The final Transportation Plan has been accepted by the Menominee Legislature and forwarded to the GTR. The draft Land Use Plan has also been forwarded to the GTR and it was confirmed that a draft would suffice to meet this deliverable. The Menominee Legislature is holding on the adoption of this plan because they want to pass it by Ordinance as is in accordance with their Constitution, and this will require some legal work beyond the scope of this grant. Additionally, the new Hearth Act Legislation was passed during the drafting of the plan that effects land tenure and the relationship between the Tribal Land Department and the BIA which implications remain to be sorted out by the Tribe’s legal department. 3.d Complete Lac du Flambeau Strategic Plan Revision and coordinate regionally. The community survey conducted by UW River Falls has been completed and the results forwarded to the GTR. Tribal Council has accepted and approved the report. A Sustainable Futures Analysis was also conducted by the Tribal Planning Department and NiiJii. Two unmet needs surveys were conducted among tribal programs (2011 and 2013. All of these studies inform the Lac du Flambeau Comprehensive Tribal Strategic Plan. A framework for demographic analysis has been developed. Basic population and poverty statistics based on the 2010 Census has been compiled along with time series information and Tribal Census information. Additional demographic analysis was provided by the Applied Population Lab at University of Wisconsin who also assisted in the development of the Tribal Unmet Needs framework called Sustainable Futures Analysis. A preliminary report has been produced. Focus Groups for the purposes of developing a comprehensive strategy plan for the Lac du Flambeau Band have been conducted with the Tribal Council, Departments of Natural Resources, Health and Welfare, Housing, Indian Child Welfare, Juvenile Justice, Domestic Abuse, Education, and Administration. A framework of strategic planning has been established. Mission, vision, goals and objectives have been determined among the groups enumerated; however, additional work remains in terms of action planning and resource assessments. The action planning segment is anticipated to take more time to complete than what was projected in the Gantt chart. A draft plan has been forwarded to the GTR. Several dates to present the Plan for adoption by Tribal Council have been postponed pending the incorporation of new evaluation information developed under the Tribe’s State of Emergency Social Services reorganization which was in response to several drug-related youth deaths. - Revised Northwoods NiiJii Comprehensive Strategic Plan Completed. The Goals and Objectives of all salient and relevant local and regional plans within the Region have been coalesced into matrices by area of emphasis in order to analyze sentiments and identify areas of future collaborations. Community groups and Neighbors have been organized in talking circles, focus groups, key contact interviews, and surveys to provide necessary public input for the development of goals objectives and prospective projects. In total 1222 community members have been engaged. These meetings include: - Through our membership in the regional business association Grow North, NiiJii has reached out to five neighboring communities (Rhinelander, Antigo, Lac du Flambeau, Crandon and Minocqua) to conduct focus groups with key stakeholders in order to solicit input regarding regional planning priorities. (Dates:3/31/11, 4/3/11, 4/11/11, 4/12/11, 4/12/11, 4/15/11, 5/1/11, 5/4/11, 59 Participants) - Extensive input with the Enterprise Community Board, staff and partners has been obtained (12/21/12 Board 11 participants, 1/23/12 Board 8 participants, 2/16/12 Board 9 participants, 6/13/12, 8 participants, 6/19/13, 9 participants, 6/20/13, 8 participants, 7/25/13, 12 participants, 8/15/12, 9 participants, 8/21/13, 11 participants, 9/11/12 staff, 9 participants, 9/12/12 staff, 9 participants, 10/26/12 Board, 10 participants, 11/7/12 staff, 9 participants). - Community Assets have been Identified and Mapped Assessment (2/1/13, 2/8/13, 4/9/13, 5/24/13, 60 participants) - Community Surveys were conducted: 8/15/13 Mole Lake, 28 respondents, Lac du Flambeau 1/17/13, 64 respondents, Cultural specific at LdF Parent Expo 57 respondents, - UW Stout Community Survey Lac du Flambeau, 4-5/2011, 522 respondents. - Special Focus Groups: Economic Development – Regional: 6/19/13 with 9 participants and 7/25/13, 12 participants EDC and Program Manager Participants. - Special Focus Group – Culture (LdF): Waaswaaganing Board 5/24/13, 8 participants, Waaswaaganing Board 4/26/13, 9 participants, Waaswaaganing Board 3/22, 9 participants, Community Focus group 2/27/13, 30 participants. - Special Focus Group – Comprehensive (Mole Lake) 8/15/13, 31 participants - Key contact Interviews: Lac du Flambeau 4/3/13, 4/11/13, 11interviews and 2 program wide unmet needs assessment surveys for Lac du Flambeau Tribal staff 60 in 2011 and 90 in 2013) - Key stakeholder Interviews: Mole Lake Chairman, 5/1/11, 1 participant. - Menominee Energy Summit Focus Group: 8/21/13, 20 program manager participants. - Grow North Regional Development Group presentation 11/14 (20 participants). The strategic plan has been drafted. North Central WI Regional Planning Commission assisted in the data compilation, mapping, drafting and publication of the document with the final professional touches and production. Rather than summarize the rather extensive document here, I reference the final output for the comprehensive regional plan. It has made substantive inroads in terms of articulating sustainable community’s goals across a wide range of socioeconomic and ethnic populations. The Plan was presented to the regional Enterprise Community Board of Directors in August and adopted in November, 2014. It was presented to Grow North Regional Development Group in November, 2014. It is currently under review with the Tribal and Municipal Governments involved and the Regional Tribal Planning designate Great Lakes Inter-tribal Council. - Equity and Opportunities Analysis In consultation with Minnesota Housing Partnership, an alternative to FHEA was developed for tribal communities which are subject to differing legal requirements. An Equity and Opportunity Analysis framework was developed which incorporated many of the tasks already undertaken to develop the comprehensive strategic plan for sustainable development. What was different about the equity and opportunity analysis was the examination of Reservation-based priorities, acknowledging the fact that as sovereign nations, these Reservation communities may have unique characteristics and circumstances and therefore different priorities that the communities expressed in the region as a whole. It was determined that each community should identify their top priorities and projects be developed to meet these specific needs. The results of this work, in conjunction with consultation from California Community and Economic Development Authority (CCEDA) is represented in Chapter 9 (pg. 170) Opportunity Analysis and Action Plan of the Northwoods NiiJii Comprehensive Strategic Plan. - Please describe the percentage completion for each of the major task categories identified in your negotiated work plan. All tasks and subtasks in the negotiated plan of work are 100% complete. - Please describe your progress with contract and sub-award management, including any issues you are experiencing or anticipating: We are not experiencing any issues. All contracts are in compliance and completed. - Please provide an update with regards to the project’s match/leverage commitments. We have exceeded our specified match requirement. - In Kind Brian Gauthier-tech asst (20 hrs. x 6 wks. x $25); Tech Assistant. Betty Jo Wozniak-staff time (9.5 hours); Time Task. Ken Clemens-labor hours (62 hours); Time Task. Lew Boyd-collaboration & labor hours (49.5 hrs.); Time Task. Paul Cegelski-labor hours (20 hours); Time Task. Joan Webster -labor hours (1.5 hours); Time Task. Eugene VanZile-TA match emergency services; Payroll Log. Jeff Ackley-hrs., project planning-housing; 130 hrs. x $37.04/hr.. Volunteers-Indian Bowl Design Team; $15/hrs.-var, people. Lake Torch Casino-conference room - 3 days; $250/day x 3 days. SCEPI-RLF funding support biz dev. program. Enterprise Comm. Board- volunteer hrs, planning; 5 hrs. x 8 people x $15. LDF Plan Dept-tech assist & proj. implementation; 661 hrs. x $21/hr.. Sokaogon Chip Comm.-EPA Grant Energy Audit; Program staff. NiiJii BOD-Strat plan TA & participation; $25/hr. x 10 pal x 3 hrs.. $25/hr. x 7 pal x 11 hrs.. Adm. Asst. 0.34 FTE SCEPI Programming; Payroll Log. Patricia O'Neil-supervisor for Patrick Wonton; 8% of time billed to HUD. MN Tribe-Housing Dept-ECRPC Meeting; meeting supplies. Lew Boyd-collaboration & labor hours (59.5 hrs.); 59.5 x $10. Lew Boyd-labor hrs. performed-see docs. SCEPI-Adm. support (Linda Wendt); 32.55 hrs. x $13. SCEPI-Consultative Services; Hrly. rate. East Central WIS Reg. Plan. Com.(pay/fringe benf.). UW Extension-Brian Gauthier-Tech Assist; 624 hrs. x $25. LDF Plan Resource Development-grant writing; 1,560 hrs. x $20. BOD Enterprise Community-meetings(travel/time); 480 hrs. x $25. LDF Plan - Director; 171.4 hrs. x $35. NiiJii BOD & staff - strategic planning meeting; 17 pal x 4 hrs. x $15. LDF Planning-office space, phone; sq. ft. x rate. Great Lakes Reg. Tribal Food Prod Summit; waived registration. LDF Band - office rental; $3562/yr. x 16 mo.. Sokaogon Chip Comm.-office rental (S.Woods); $6300/yr. x 16 mo.. MN Tribe - TA Hours for project; various. VISTA-Patrick Wontor-hrs-proj implementation; 1/3 of total $83,440. Eugene VanZile-TA hrs-vol time coor council; $25/hr. x 40 hrs.. SCEPI - inkind project administrative services. MN Tribe - addt items. Lew Boyd - labor hrs. worked MITW; 168 hours. Ken Klemens - labor hrs. worked MITW; 26 hours. East Central WIS Reg. Plan Com(photocopy). Lew Boyd - 8.15.12 meeting and supplies; 12 x $50 x 3 hrs.. - 9.05.12 meeting and supplies; 12 x $50 x 3 hrs.. - 10.10.12 meeting and supplies; 12 x $50 x 3 hrs.. - Ken Klemens hours; 22 hrs. - salary/fringe. - Paul Cegelski hours; 124 hrs. x $50/hr.. - Lew Boyd - already submitted; 87 hrs. x $50/hr.. SCEPI Loans; $300,000. SCEPI Community Foundation Grant; $26,000. Sue Thering/Design Coalition; $300. North Central WI Regional Planning Commission; $5,000. - Please describe progress with outreach, engagement, and decision-making activities targeting populations traditionally marginalized in the planning process (include costs spent on these activities): Outreach is described in a. above. 100% of our population is marginalized. Targeting has been community based and generally accompanied by a meal.

- CHALLENGES AND EFFORTS TO OVERCOME THEM:

- Scheduled Milestones/Targets that were not achieved: None. - Management deficiencies: Lost Program Manager/Planner due to illness. Time supplemented by Executive Director and Transportation Planner. - Deviations from the Work Plan Expand Indian Bowl Feasibility to include both business analysis and capital campaign feasibility with permission from GTR. Unable to complete funding for the Mole Lake Fire and Emergency Services facility at this time because the Sokaogon Chippewa Community has placed a hold on match funding and declined to pursue grants at this time due to unforeseen economic constraints within the Tribe (land and facility owner). - Detail the actions you will take to address identified deficiencies or work plan deviations described above (include what is to be done, who is responsible, and when it is due). None.